## Executive Summary
Ares Existing Tools Reliability Upgrade Plan
Senior-planner audit ¦ Existing tools only ¦ 2026-07-10
Outcome | 68 public Ares tools inventoried; 29 prioritized upgrade rows; 18 evidence-backed defects/risks; no new public tool names or net-new product features proposed.
Verification | 223 focused tests passed and 2 skipped in 73.44s. The full suite did not finish inside the 120-second audit window, so this workbook does not claim a globally green suite.
False-negative posture | The audit combines full tool-schema inventory, implementation tracing, current tests, prior upgrade notes, static failure-path review, and targeted repros. No finite review proves that no other bugs exist; unconfirmed findings are labeled code-backed rather than confirmed.
Highest-risk cluster | False success/rollback in batch_edit; lost output and non-persistent Windows execution; MCP error/readiness semantics; web evidence loss; memory recall misses; cron/config concurrent state corruption.
Scope boundary | Upgrade and bug-fix existing behavior only. Preserve existing safety controls and permissions; do not add new guardrails as product scope, and do not remove current controls.
North star | Ares behaves like a dependable JARVIS: accurate perception, durable memory, trustworthy action, explicit failure, self-recovery, temporal awareness, and transparent multi-step execution.
P0 Definition of Done
1. Reproduce first | Each P0 fix begins with a deterministic failing regression test.
2. Preserve compatibility | Keep public tool names and intended outputs stable; document any unavoidable error-shape correction.
3. Prove failure paths | Fault injection verifies rollback, timeout, cancellation, partial I/O, and concurrent mutation behavior.
4. System journey | Pass end-to-end journeys that chain existing tools; zero silent success and zero orphaned state.

## Upgrade Roadmap
ID | Priority | Phase | Existing Tool | Category | Evidence Status | Weakness / Bug | Upgrade / Fix (No New Feature) | Why Important | Contribution to Iron Man JARVIS | Acceptance Test / Definition of Done | Repository Evidence | Effort | Owner | Dependencies
ARES-001 | P0 | 1 | batch_edit | File operations | Confirmed by repro | An edit with no matching text is reported as a completed batch. Directory move/copy snapshots cannot be fully restored, so a later failure can leave the source missing and destination present even while the tool says it rolled back. | Return typed per-operation success/failure, fail the transaction on unsuccessful tool results, and snapshot/restore directory trees plus overwritten targets atomically. Roll back backup/index side effects with the same transaction. | Multi-step autonomous work is only trustworthy when success and rollback claims match disk state. | Gives Ares dependable multi-file execution: plan, act, verify, and recover without silent workspace corruption. | A no-match edit fails the batch; an injected failure after a directory move restores source and destination byte-for-byte; no orphan files, directories, or backup-index rows remain. | ares/tools/filesystem_write.py:272; targeted repro 2026-07-10 | L (7-10d) | Core Runtime | ARES-002
ARES-002 | P1 | 2 | edit_file | File operations | Confirmed code path | Whitespace-normalized edits rebuild content with LF, changing CRLF files. Backup index entries are recorded before the backup copy exists, allowing dangling restore points after copy failure. | Preserve the detected newline convention and trailing-newline state in every edit path. Create and fsync the backup first, then append the index atomically; return an explicit changed/unchanged result. | Invisible line-ending churn and invalid backups create noisy diffs and unreliable recovery. | Makes Ares a precise coding partner that can modify existing code without collateral formatting changes. | CRLF and LF fixtures retain their original style; a forced backup-copy failure leaves no index row; exact and whitespace-normalized paths share the same result contract. | ares/tools/filesystem_write.py:95; ares/tools/filesystem_write.py:567 | M (3-5d) | Core Runtime | ARES-001
ARES-003 | P1 | 2 | search_files | File discovery | Confirmed code path | Inside an active event loop the sync wrapper starts a thread and immediately joins it, blocking the loop. Results are de-duplicated by file path, so additional useful line matches in the same file disappear. | Route the public tool through search_files_async from execute_async, keep multiple ranked line hits per file within the cap, and report both matched files and matched lines. | Blocking search stalls streaming and dropped matches increase false negatives during code diagnosis. | Improves Ares's perception loop: faster navigation and more complete evidence before it edits or explains code. | A concurrent heartbeat continues during a large search; three matches in one file remain visible; caps and ignore behavior stay deterministic. | ares/tools/filesystem.py:406; ares/tools/filesystem.py:454; ares/tools/executor.py:162 | M (3-5d) | Retrieval | None
ARES-004 | P2 | 3 | read_file | File discovery | Code-backed scalability risk | The tool reads the entire file into memory before returning a small requested slice. Large logs or generated files cause avoidable latency and memory pressure. | Stream to the requested window, bound symbol-context scanning, and compute totals without retaining all content. Preserve current line numbering and context output. | A local assistant must inspect large workspaces without freezing the interaction loop. | Lets Ares observe large files quickly and keep more working memory for reasoning. | A 1 GB synthetic file returns a 200-line slice within a fixed memory budget; line numbers, context, and above/below counts remain correct. | ares/tools/filesystem.py:91 | M (3-5d) | Retrieval | None
ARES-005 | P2 | 3 | get_file_info | File discovery | Confirmed code path | resolve_path follows symlinks before get_file_info checks is_symlink, so symlinks are normally reported as their target type. | Retain the lexical path, use lstat for link metadata, then separately report the resolved target and target status. | Wrong file identity can lead to incorrect explanations and edits in linked worktrees or shared assets. | Improves environmental awareness: Ares understands what an object is before acting on it. | File, directory, valid symlink, and broken symlink fixtures report the correct type and target on supported platforms. | ares/tools/filesystem.py:56; ares/tools/filesystem.py:522 | S (1-2d) | Retrieval | None
ARES-006 | P2 | 3 | disk_usage | File discovery | Code-backed scalability risk | Each displayed directory recursively re-scans its full subtree, producing repeated I/O that approaches O(files x displayed depth). File input also falls through to a misleading zero-byte directory result. | Walk once, aggregate sizes bottom-up, apply the same ignore policy as file search, and return a clear file result when path is a file. | Repeated scans make routine storage diagnosis slow on large repositories. | Gives Ares fast situational awareness of workspace size and storage hotspots. | Instrumentation proves each file is stat'ed once; totals match a reference walk; file input reports the actual file size. | ares/tools/filesystem.py:609 | M (3-5d) | Retrieval | None
ARES-007 | P2 | 3 | find_duplicates | File discovery | Code-backed scalability risk | Every same-size candidate is fully MD5-hashed and only hard-coded noisy directories are skipped. Large trees incur unnecessary reads and ignore-file expectations differ from search_files. | Use staged comparison (size, prefix/suffix sample, then full SHA-256 only for survivors), share ignore handling, and clamp input limits consistently. | Duplicate discovery should not monopolize disk I/O or surprise users with inconsistent scope. | Makes Ares efficient at housekeeping and storage optimization while keeping results exact. | Duplicate groups match the current reference result; measured bytes read fall materially on non-duplicate fixtures; .gitignore behavior matches search_files. | ares/tools/filesystem.py:750 | M (3-5d) | Retrieval | None
ARES-008 | P0 | 1 | web_search | Web research | Confirmed by repro | Provider date fields are discarded during normalization, so freshness is always 'undated'. Host quality uses substring checks, mislabeling domains such as github.com.evil.example. Synchronous fetch failures can disappear instead of entering errors. | Preserve date and provider metadata, match exact/parent hostnames, record every fetch outcome, and fetch the bounded top set concurrently while preserving result order. | Research quality labels currently look authoritative while losing the evidence needed to justify them. | Moves Ares toward JARVIS-grade research: current, source-aware, transparent, and fast. | Dated fixtures remain dated; lookalike hosts are not promoted; each failed top-result fetch is represented; result order and caps remain stable. | ares/tools/web.py:33; ares/tools/web.py:157; ares/tools/web.py:272; targeted repro 2026-07-10 | L (6-8d) | Research | ARES-009
ARES-009 | P0 | 1 | fetch_url | Web research | Confirmed code path | The 2 MB limit is applied after client.get has downloaded the complete body. HTML/text can be sliced at the cap without setting truncated, and the public error wrapper drops status, final URL, and retryability metadata. | Stream response bytes and stop at the cap, separate byte and character truncation, set truncation on every capped path, and retain status/final URL/retryability in error output. | Large downloads can exhaust memory, and lost error metadata prevents intelligent retry decisions. | Enables bounded, self-correcting web perception: Ares knows what failed and whether to retry. | A 10 MB fixture reads no more than cap plus one chunk and returns truncated=true; 429/5xx/redirect failures retain status, final URL, and retryability. | ares/tools/web.py:488; ares/tools/web.py:595 | M (4-5d) | Research | None
ARES-010 | P0 | 1 | search_memory | Memory | Confirmed by repro | Malformed FTS syntax such as an unbalanced quote is swallowed and returns no match when vector search is unavailable. Session filtering occurs after a small global top-N vector query, which can exclude relevant scoped memories before filtering. | Add a deterministic escaped/literal FTS fallback, apply scope before or during candidate ranking, and expose degraded search mode internally for observability. | False-negative recall makes the assistant contradict known preferences or repeatedly ask answered questions. | Creates dependable long-term recall, a core JARVIS behavior: relevant personal context appears when needed. | The query "favorite finds a stored matching fact with vector search disabled; scoped search fills the requested limit when qualifying memories exist. | ares/memory.py:276; targeted repro 2026-07-10 | L (6-8d) | Memory | ARES-011
ARES-011 | P1 | 2 | update_memory | Memory | Confirmed code path | Ranking treats confidence 0.0 as 1.0 because it uses value-or-default, giving explicitly untrusted memories the full confidence boost. | Distinguish None from zero, clamp stored confidence/importance to the existing numeric domain, and add deterministic ranking fixtures. | A low-confidence memory should not outrank verified user facts. | Improves judgment: Ares weighs its memory by trust instead of merely retrieving text. | Otherwise-identical confidence=0 and confidence=1 memories rank in the correct order; zero remains zero through store, update, and reload. | ares/memory.py:254 | S (1-2d) | Memory | ARES-010
ARES-012 | P0 | 1 | export_data | Data portability | Confirmed by repro + code path | Profile lookup is case-insensitive but the exported profile label is case-sensitive (MEMORIES is labeled full). Redaction only excludes two top-level keys; arbitrary MCP server config can contain nested tokens, client secrets, or secret environment values. | Normalize the profile once, recursively redact credential-like config keys while preserving structure, and use collision-safe/atomic output naming. Keep existing export profiles and schema compatible. | Incorrect labels break restore confidence; credential leakage turns a backup into a liability. | Makes Ares portable and dependable across machines without corrupting or exposing its operating context. | Every case variant labels and exports the same profile; nested secret fixtures are redacted; two exports in one second create distinct valid JSON; write failure leaves no partial file. | ares/tools/exporter.py:31; targeted repro 2026-07-10 | M (4-5d) | Data Platform | None
ARES-013 | P0 | 1 | run_code | Execution | Confirmed by repro | Child-process and file-descriptor-level stdout bypass StringIO, appear before the protocol JSON, and are discarded by the result reader. A successful subprocess print can therefore return 'Executed successfully (no output)'. | Capture OS-level stdout/stderr separately from the control protocol, frame results with a robust channel, and restart cleanly after timeout or protocol corruption while preserving the existing pinned namespace. | Missing output causes false success and prevents Ares from verifying builds, scripts, and diagnostics. | Provides a trustworthy execution-observation loop: run, see the real result, reason, and continue. | subprocess print, sys.stdout.buffer, Unicode, large output, exception, and timeout fixtures all return complete bounded results; namespace persistence remains intact. | ares/tools/repl.py:40; ares/tools/repl.py:180; targeted repro 2026-07-10 | L (7-10d) | Core Runtime | None
ARES-014 | P0 | 1 | run_command | Execution | Confirmed by repro | On Windows each call uses a fresh subprocess while an unused cmd.exe remains open, so cd and environment changes do not persist despite the tool's persistent-session contract. Timeout kills the immediate process but can leave descendants. | Use one real long-lived PowerShell/cmd protocol on Windows, preserve cwd/environment across calls, capture Unicode deterministically, and terminate the full process tree on reset/timeout. | State loss and orphan processes make multi-step build and automation work nondeterministic. | Gives Ares a reliable hands-and-eyes loop for sustained terminal work, closer to JARVIS operating a workstation. | Set-then-read environment and cd-then-pwd persist across calls; timeout removes descendants; reset clears state; Unicode and exit codes round-trip exactly. | ares/tools/repl.py:128; ares/tools/repl.py:299; targeted repro 2026-07-10 | L (8-10d) | Core Runtime | None
ARES-015 | P0 | 1 | terminal_exec | Execution | Confirmed shared defect | terminal_exec uses the same broken Windows shell runtime as run_command and additionally treats terminal display as best-effort without reporting whether the visible panel received the command. | Move it onto the corrected shell session, preserve identical execution semantics with run_command, and return a non-fatal display-delivery status alongside the command result. | The visible terminal must agree with the captured execution or the user cannot supervise long-running work. | Creates transparent workstation control: Ares can act while the user sees the same command and outcome. | Execution output matches run_command for the same command; display callback success/failure is observable; callback failure never changes command success. | ares/tools/executor.py:748 | M (3-4d) | Desktop Runtime | ARES-014
ARES-016 | P0 | 1 | Existing MCP tools (mcp__*) | Integrations | Confirmed by repro + code path | MCP CallToolResult.isError is ignored and server error text is returned as normal content. Failed health probes leave sessions marked ready; cancelled connects can return without a session or recorded error. Startup is sequential across servers. | Propagate MCP error semantics, mark failed probes degraded/not-ready, make cancelled connect an explicit failure, and connect/probe independent servers concurrently with per-server timeouts. | External actions are only useful if Ares can distinguish success from failure and isolate one unhealthy integration. | Makes the tool ecosystem dependable: JARVIS can use many connected services without one failure poisoning the control loop. | isError results return an error state; probe failure flips readiness; cancellation is visible; one 60-second server does not block healthy servers from becoming ready. | ares/tools/mcp_client.py:385; ares/tools/mcp_client.py:511; ares/tools/mcp_client.py:632; targeted repro 2026-07-10 | L (7-9d) | Integrations | None
ARES-017 | P1 | 2 | generate_image | Media | Confirmed code path | The filename hashes only the prompt, so the same prompt with a different seed, model, or size overwrites the prior result. Image content is trusted from Content-Type, and a manifest-write failure makes a successfully saved image look like a failed generation. | Key output identity on all generation inputs (or content checksum), validate the decoded image before success, save atomically, and report manifest failure as a warning without hiding the valid asset. | Silent overwrites destroy reproducibility and false negatives can trigger duplicate generation attempts. | Lets Ares create, compare, and reuse visual assets reliably as part of a longer workflow. | Same prompt with different seed/size/model yields distinct paths; corrupt image bytes fail before success; manifest failure preserves and reports the valid image path. | ares/tools/image_generate.py:18; ares/tools/asset_manifest.py:56 | M (3-5d) | Media | None
ARES-018 | P1 | 2 | resize_image | Media | Confirmed code path | Zero/negative dimensions are accepted until Pillow fails, source overwrite is non-atomic, and animated images collapse to the loaded frame. | Validate positive computed dimensions, preserve supported animation frames and timing, and write to a verified temp file before atomic replace. | A resize should never corrupt the source or silently destroy animation. | Makes visual transformation reliable enough for autonomous asset preparation. | Invalid dimensions return a precise error before writing; injected save failure leaves source checksum unchanged; animated GIF frame count and durations remain intact. | ares/tools/image_edit.py:68 | M (4-5d) | Media | None
ARES-019 | P1 | 2 | convert_image | Media | Confirmed code path | Animated input is reduced to one frame, quality is not bounded to its documented range, and output format can disagree with the caller-supplied extension. Overwrites are non-atomic. | Preserve frames for animation-capable targets, validate quality, reconcile/validate output extension with format, and use temp-save plus atomic replace. | Silent frame loss and ambiguous file types break downstream preview and upload steps. | Improves multimodal workflow continuity: assets remain valid and predictable across conversions. | Animated GIF/WebP fixtures retain frames where supported; quality 0/101 is rejected clearly; saved signature and reported format agree; failed overwrite preserves source. | ares/tools/image_edit.py:147 | M (4-5d) | Media | None
ARES-020 | P1 | 2 | crop_image | Media | Confirmed by repro | Bounds are validated before clamping, so a rectangle entirely outside the image becomes a zero-area crop and fails later with 'cannot write empty image'. Source overwrite is non-atomic. | Clamp first, then validate non-zero intersection with a domain-specific error; save via temp file and atomic replace; preserve animation rules consistently with other image tools. | Precise spatial operations need predictable coordinates and must not endanger the original asset. | Gives Ares accurate visual manipulation and clear self-correction when coordinates are wrong. | Outside/edge/negative/valid rectangles produce deterministic results; no zero-area image reaches Pillow save; forced save failure leaves source unchanged. | ares/tools/image_edit.py:223; targeted repro 2026-07-10 | S (2d) | Media | ARES-018
ARES-021 | P0 | 1 | create_cron_job / update_cron_job | Automation | Confirmed code path | Cron jobs use unlocked read-modify-write JSON storage. Concurrent scheduler, manual, or UI updates can overwrite each other even though each individual file replace is atomic. | Add a cross-process file lock and revision-aware mutation API, validate the complete updated job before commit, and keep atomic replace as the final write. | Lost schedules or state updates make proactive automation untrustworthy. | Provides durable planning: Ares can maintain recurring work without races or disappearing jobs. | Parallel create/update/run-count stress tests preserve every committed mutation and always leave valid JSON; stale revision attempts retry or fail explicitly. | ares/cron/store.py:26 | L (6-8d) | Automation | None
ARES-022 | P0 | 1 | run_cron_job_now | Automation | Confirmed code path | When called inside an event loop the tool launches an untracked background task and immediately reports started. Invalid IDs and runner failures can become unobserved task exceptions; duplicate manual/scheduled runs can execute concurrently. | Register every run task, perform an atomic scheduled-to-running transition, reject/coalesce duplicate runs, and persist terminal status/log path even when setup or finalization fails. | Autonomous jobs must have exactly-once visible state rather than ambiguous background execution. | Moves Ares toward proactive JARVIS behavior with observable, recoverable scheduled actions. | Invalid IDs fail synchronously; duplicate trigger returns already-running; every accepted run reaches completed/failed with one log and one run-count increment. | ares/cron/tools.py:30; ares/cron/runner.py:29 | L (6-8d) | Automation | ARES-021
ARES-023 | P1 | 2 | get_cron_job | Automation | Confirmed code path | A process crash after state='running' leaves a job permanently skipped. Missed-run simulation caps at 100 without saying the count was truncated, which can understate backlog. | Represent running state with a lease/heartbeat recoverable at startup, and include a capped/truncated indicator in the existing schedule simulation output. | Stuck jobs and understated backlog hide failures from both the user and the planner. | Adds self-recovery and honest schedule awareness to proactive automation. | Expired running leases return to scheduled/failed deterministically; simulations over 100 missed runs report lower bound plus truncated=true. | ares/cron/store.py:68; ares/cron/schedule_utils.py:102; ares/cron/runner.py:32 | M (4-5d) | Automation | ARES-021
ARES-024 | P1 | 2 | phone_status | Phone control | Confirmed code path | Top-level ok requires both KDE Connect and ADB, even when one capability set is usable. KDE status can be ok while unreachable, contacts/SMS capability ignores reachability, and the auto-discovered device ID is cached indefinitely. | Derive status per capability, require current reachability for KDE actions, expose any-ready versus fully-ready clearly, and invalidate device discovery on config/status changes or failed action. | A single false status can make the agent avoid a working action or attempt an unavailable one. | Improves embodied awareness: Ares knows exactly which phone actions are possible right now. | KDE-only, ADB-only, unreachable, re-paired, and multi-device fixtures produce correct capability states and action routing. | ares/tools/kdeconnect_bridge.py:58; ares/tools/kdeconnect_bridge.py:72; ares/tools/adb_bridge.py:98 | M (3-5d) | Device Platform | None
ARES-025 | P1 | 2 | phone_get_notifications / phone_search_contact | Phone control | Confirmed code path | CLI output is parsed as one notification/contact per line with fixed separators; multiline and version-specific output can be split or dropped. Limits are not consistently bounded, and subprocess timeout/Unicode decode failures propagate instead of returning tool errors. | Add versioned fixture-driven parsers, bound result limits, use explicit encoding/error handling, and convert timeout/OS failures into the existing structured JSON error shape. | Private device context must be complete and correctly attributed before Ares summarizes or acts on it. | Gives JARVIS-like ambient awareness without confusing senders, apps, titles, or contact numbers. | Unicode and multiline fixtures from supported KDE versions parse correctly; timeout and missing-device cases return ok=false JSON; requested caps are enforced. | ares/tools/kdeconnect_bridge.py:98; ares/tools/kdeconnect_bridge.py:119 | M (4-5d) | Device Platform | ARES-024
ARES-026 | P1 | 2 | get_current_datetime | Time | Confirmed by repro | An invalid requested timezone silently returns UTC, making a bad input look like a valid answer for another zone. Related date parsing accepts timezone_name but converts the result to the machine's local zone. | Return an explicit invalid-timezone error for bad names and consistently preserve the requested timezone in parsing and output. | Time mistakes cascade into reminders, cron jobs, travel plans, and user trust. | Gives Ares precise temporal awareness, essential for JARVIS-style planning and proactive execution. | Invalid zone never masquerades as UTC; valid IANA zones round-trip exactly; parsing 09:00 America/New_York returns that zone rather than the machine zone. | ares/tools/datetime_tool.py:10; ares/tools/dates.py:40; targeted repro 2026-07-10 | S (1-2d) | Core Runtime | ARES-021
ARES-027 | P0 | 1 | update_config | Configuration | Confirmed code path | Empty/unknown paths and wrong value types are written without validating the resulting AppConfig. A later load can reject the file and fall back to defaults, so one surgical update can effectively reset unrelated runtime behavior. | Apply the patch to a copy, validate the full AppConfig, atomically commit only valid data, and return field-level validation errors while preserving the original file byte-for-byte on failure. | Configuration is the control plane; silent invalidation can disable models, tools, phone, or automation unexpectedly. | Makes Ares self-configuring without destabilizing its existing operating state. | Empty path, unknown field, and wrong type fail without changing the file; valid nested updates preserve all sibling fields and reload identically. | ares/config.py:103; ares/tools/executor.py:823 | M (3-4d) | Core Runtime | None
ARES-028 | P2 | 3 | write_file | File operations | Confirmed code path | User-facing size messages call len(content) bytes even though that is a character count, so non-ASCII files report the wrong size. The low-level implementation can overwrite directly when called outside the executor's confirmation wrapper. | Report encoded byte length and centralize overwrite/atomic behavior in one implementation path so every caller receives identical result semantics. | Precise file telemetry and a single behavior path reduce hidden divergence between CLI, agent, and tests. | Improves execution confidence: Ares reports what it actually wrote and behaves consistently across surfaces. | UTF-8 fixtures report actual bytes; executor and direct implementation share the same overwrite result contract; existing atomic-write tests remain green. | ares/tools/filesystem_write.py:44; ares/tools/executor.py:443 | S (1-2d) | Core Runtime | None
ARES-029 | P1 | 2 | copy_file | File operations | Code-backed reliability risk | Copy writes directly to the destination, so interruption or disk failure can leave a partial file. Overwrite success is not verified against source size/checksum. | Copy to a same-filesystem temp path, fsync, preserve metadata, atomically replace the destination, and verify size (plus checksum when requested internally) before reporting success. | A partial copy reported as success can poison later edits, exports, or duplicate analysis. | Makes Ares's workspace manipulation reliable enough for unattended multi-step tasks. | Injected mid-copy failure leaves the old destination intact; success matches source size and bytes; metadata preservation tests pass. | ares/tools/filesystem.py:716 | M (3-4d) | Core Runtime | None

## Bug Evidence
Bug ID | Severity | Tool / Subsystem | Validation | Expected | Observed | Fix Direction | Regression Test | Evidence
BUG-001 | Critical | batch_edit | Reproduced | No-match edit fails transaction | Batch reports completed while file is unchanged | Typed operation status and fail-fast transaction | No-match edit causes rollback | filesystem_write.py:272; repro 2026-07-10
BUG-002 | Critical | batch_edit | Reproduced | Failed directory move batch restores source | Source stays missing and destination remains after reported rollback | Directory-aware snapshots and restore | Injected failure after directory move | filesystem_write.py:288; repro 2026-07-10
BUG-003 | High | web_search | Reproduced | Provider publish date survives normalization | Date field is dropped and source is labeled undated | Preserve normalized metadata | Dated Tavily/DDGS fixture | web.py:33; repro 2026-07-10
BUG-004 | High | web_search | Reproduced | Only exact/trusted host is promoted | github.com.evil.example is labeled primary-or-technical | Exact hostname/parent-domain matching | Lookalike-host fixture | web.py:157; repro 2026-07-10
BUG-005 | High | get_current_datetime | Reproduced | Invalid zone returns an error | Mars/Olympus silently returns UTC | Explicit ZoneInfo validation result | Invalid-zone fixture | datetime_tool.py:10; repro 2026-07-10
BUG-006 | High | Date parsing | Reproduced | Requested America/New_York zone is retained | Result is converted to machine zone +05:30 | Convert/output in requested zone | Cross-zone parsing matrix | dates.py:40; repro 2026-07-10
BUG-007 | Medium | crop_image | Reproduced | Out-of-image crop returns domain error before save | Returns Pillow 'cannot write empty image' | Clamp then validate intersection | Outside-bounds crop fixtures | image_edit.py:223; repro 2026-07-10
BUG-008 | Critical | MCP call execution | Reproduced | isError result is surfaced as error | Server-side failure text is returned as normal content | Propagate CallToolResult.isError | Fake MCP isError result | mcp_client.py:632; repro 2026-07-10
BUG-009 | Critical | run_code | Reproduced | Child process stdout is returned | Successful child print returns no output | Separate control and OS output channels | subprocess/sys.stdout.buffer fixtures | repl.py:40; repro 2026-07-10
BUG-010 | Critical | run_command | Reproduced on Windows | Environment persists across calls | Second call echoes literal %ARES_PERSIST_CHECK% | Real persistent Windows shell | Two-call env/cwd test | repl.py:128; repro 2026-07-10
BUG-011 | High | search_memory | Reproduced | Malformed FTS-like user text still finds literal match | Unbalanced quote returns zero results with vector disabled | Escaped/literal FTS fallback | Malformed quote/operator corpus | memory.py:276; repro 2026-07-10
BUG-012 | Medium | Memory bulk delete | Reproduced | Deleted count equals rows actually removed | One real + one missing ID reports 2 | Use cursor rowcount/RETURNING | Mixed existing/missing IDs | memory.py:396; repro 2026-07-10
BUG-013 | Medium | export_data | Reproduced | MEMORIES profile labels itself memories | Payload is labeled full | Normalize profile once | Case-variant profiles | exporter.py:31; repro 2026-07-10
BUG-014 | High | fetch_url | Static path confirmation | 2 MB cap bounds network read | client.get downloads full body before slicing | Stream and stop at cap | 10 MB local HTTP fixture | web.py:517
BUG-015 | High | MCP health | Static path confirmation | Failed probe makes server not-ready/degraded | Session remains in sessions and readiness stays ready | Update readiness state on probe failure | Timeout/error probe fixture | mcp_client.py:511
BUG-016 | High | Cron store | Static path confirmation | Concurrent mutations are serialized | Unlocked read-modify-write can lose updates | Cross-process lock + revision | Parallel mutation stress test | cron/store.py:26
BUG-017 | High | phone_status | Static path confirmation | Capabilities require current reachability | Paired-but-unreachable can show contacts/SMS capable | Capability-level live health | Reachability/config-change fixtures | kdeconnect_bridge.py:72; adb_bridge.py:121
BUG-018 | Medium | get_file_info | Static path confirmation | Symlink is reported as symlink | Resolved path normally reports target type | lstat lexical path before resolve | Symlink and broken-link fixtures | filesystem.py:56; filesystem.py:522

## Tool Inventory
# | Existing Tool | Category | Current Purpose | Implementation | Roadmap ID | Audit Status
1 | store_memory | Memory | Save a durable user preference, identity fact, recurring project, or explicit remember-this request. Do not store temporary moods, insults, tool outputs, guesses, current events, or facts about the world. | ares/memory.py; ares/tools/executor.py | ARES-010 | Prioritized in roadmap
2 | search_memory | Memory | Search stored user memories before relying on or updating remembered user facts. | ares/memory.py; ares/tools/executor.py | ARES-010 | Prioritized in roadmap
3 | update_memory | Memory | Correct or enrich an existing stored memory when the user updates a durable preference or an old memory is wrong. | ares/memory.py; ares/tools/executor.py | ARES-011 | Prioritized in roadmap
4 | delete_memory | Memory | Forget a stored memory by ID. | ares/memory.py; ares/tools/executor.py | ARES-011 | Prioritized in roadmap
5 | list_skills | Skills | Inspect available reusable skills/playbooks. Use only when the user asks about skills or discovery is necessary; do not narrate skill selection. | ares/skills.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
6 | load_skill | Skills | Internal helper: load a skill's full SKILL.md instructions when needed, then follow it silently to complete the current request. | ares/skills.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
7 | create_skill | Skills | Save a reusable workflow as a local Ares skill. | ares/skills.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
8 | export_data | Data portability | Export local Ares memories, conversations, and config to JSON, with selective profiles and redaction preview. | ares/tools/exporter.py | ARES-012 | Prioritized in roadmap
9 | web_search | Web research | Search the web and automatically read top results. Can prefer the Fetch MCP server when connected, with local fetch_url fallback. | ares/tools/web.py | ARES-008 | Prioritized in roadmap
10 | fetch_url | Web research | Fetch a page/PDF/text URL and extract readable content plus metadata such as final URL, canonical URL, description, status, truncation, and retryability. | ares/tools/web.py | ARES-009 | Prioritized in roadmap
11 | read_file | File discovery | Read a local text file with line numbers and automatic nearby imports/classes/functions/heading context for code or markdown slices. | ares/tools/filesystem.py | ARES-004 | Prioritized in roadmap
12 | search_files | File discovery | Search local files by content and/or file name glob pattern using ripgrep when available, ranked results, snippets, and ignore-file awareness. | ares/tools/filesystem.py | ARES-003 | Prioritized in roadmap
13 | list_directory | File discovery | List a local directory with file sizes and subdirectories. | ares/tools/filesystem.py |  | Inventoried; no confirmed critical defect in this pass
14 | get_file_info | File discovery | Get metadata about a file or directory: type, size, timestamps, binary status. | ares/tools/filesystem.py | ARES-005 | Prioritized in roadmap
15 | glob_pattern | File discovery | Find files matching a glob pattern (e.g. **/*.py, src/**/*.ts). | ares/tools/filesystem.py |  | Inventoried; no confirmed critical defect in this pass
16 | write_file | File operations | Create a NEW file or FULLY OVERWRITE an existing one. Dry runs include a patch preview for overwrites. NEVER use for adding/inserting text into an existing file. For adding/inserting: use edit_file (find+replace), insert_line (by line number), append_to_file (end), prepend_to_file (start), or batch_file_ops. If overwriting, confirm=true is required. | ares/tools/filesystem_write.py; ares/tools/executor.py | ARES-028 | Prioritized in roadmap
17 | edit_file | File operations | Edit a file by searching and replacing text with diff preview, conflict hints, and backup creation. Great for targeted changes without touching the rest of the file. old_text must match uniquely. If no match, returns the closest content as a suggestion. | ares/tools/filesystem_write.py; ares/tools/executor.py | ARES-002 | Prioritized in roadmap
18 | create_directory | File operations | Create a directory and any missing parent directories (mkdir -p). | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
19 | delete_file | File operations | Delete a file or empty directory. Always requires confirm=true. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
20 | move_file | File operations | Move or rename a file or directory. Creates parent directories of destination as needed. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
21 | batch_edit | File operations | Execute multiple file operations transactionally with rollback on partial failure. Supports write, edit, delete, move, copy, and mkdir/create_directory actions with per-operation results. | ares/tools/filesystem_write.py; ares/tools/executor.py | ARES-001 | Prioritized in roadmap
22 | glob_apply | File operations | Apply a safe bulk action to files matching a glob pattern. Defaults to dry_run=true. Supports list, delete, move, and copy. | ares/tools/filesystem_write.py; ares/tools/executor.py | ARES-001 | Prioritized in roadmap
23 | show_file_with_line_numbers | File operations | Show a text file with stable 1-based line numbers before line-based edits. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
24 | insert_line | File operations | Insert text before or after a 1-based line number. Makes an automatic backup before editing and supports dry_run diff preview. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
25 | replace_lines | File operations | Replace an inclusive 1-based line range. Makes an automatic backup before editing and supports dry_run diff preview. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
26 | delete_lines | File operations | Delete an inclusive 1-based line range. Makes an automatic backup before editing and supports dry_run diff preview. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
27 | preview_diff | File operations | Preview a unified diff for replacing a file with new_content without changing the file. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
28 | backup_file | File operations | Create a named timestamped .ares_backups restore point and backup index entry for a file. | ares/tools/filesystem_write.py; ares/tools/executor.py | ARES-002 | Prioritized in roadmap
29 | undo_last_edit | File operations | Restore the newest backup for a file from its .ares_backups folder. | ares/tools/filesystem_write.py; ares/tools/executor.py | ARES-002 | Prioritized in roadmap
30 | batch_file_ops | File operations | Run line-based file operations atomically with rollback if any operation fails. Supports insert_line, replace_lines, delete_lines, append, and prepend. | ares/tools/filesystem_write.py; ares/tools/executor.py | ARES-001 | Prioritized in roadmap
31 | find_text | File operations | Find text in one file and return matching line numbers with nearby context. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
32 | append_to_file | File operations | Append text to a file with backup, diff preview, and dry_run support. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
33 | prepend_to_file | File operations | Prepend text to a file with backup, diff preview, and dry_run support. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
34 | compare_files | File operations | Compare two text files and return a unified diff. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
35 | create_file_from_template | File operations | Create a new file from a built-in template: python, html, readme, notes, school_essay, or homework. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
36 | safe_path_status | File operations | Check whether a file path is considered safe or blocked as a dangerous system path. | ares/tools/filesystem_write.py; ares/tools/executor.py |  | Inventoried; no confirmed critical defect in this pass
37 | disk_usage | File discovery | Show disk usage for a directory tree with sizes and file counts (like du -sh). | ares/tools/filesystem.py | ARES-006 | Prioritized in roadmap
38 | checksum | File discovery | Compute file checksum hash (md5, sha1, sha256, sha512). Useful for verifying file integrity. | ares/tools/filesystem.py |  | Inventoried; no confirmed critical defect in this pass
39 | copy_file | File operations | Copy a file to a new location. | ares/tools/filesystem_write.py; ares/tools/executor.py | ARES-029 | Prioritized in roadmap
40 | find_duplicates | File discovery | Find duplicate files by size and content hash. Useful for cleaning up redundant files. | ares/tools/filesystem.py | ARES-007 | Prioritized in roadmap
41 | tail_file | File discovery | Read the last N lines of a file (like Unix tail). | ares/tools/filesystem.py |  | Inventoried; no confirmed critical defect in this pass
42 | head_file | File discovery | Read the first N lines of a file (like Unix head). | ares/tools/filesystem.py |  | Inventoried; no confirmed critical defect in this pass
43 | count_lines | File discovery | Count lines in files with optional content and name filtering (like wc -l). | ares/tools/filesystem.py |  | Inventoried; no confirmed critical defect in this pass
44 | file_tree | File discovery | Display directory tree structure (like the tree command). | ares/tools/filesystem.py |  | Inventoried; no confirmed critical defect in this pass
45 | run_code | Execution | Execute Python code in the pinned persistent Python runtime session. Full access to stdlib, pip, filesystem, network. Supports reset checkpoints and dependency fingerprints. | ares/tools/repl.py; ares/tools/executor.py | ARES-013 | Prioritized in roadmap
46 | run_command | Execution | Execute a shell command (bash, git, npm, python, docker, etc.) in the pinned persistent shell session. Supports command profiles, timeout hints, structured summaries, pipes, redirects, && chaining. DO NOT use for phone operations — use phone_status, phone_get_notifications, phone_send_sms, phone_call_number, or phone_search_contact instead. | ares/tools/repl.py; ares/tools/executor.py | ARES-014 | Prioritized in roadmap
47 | generate_image | Media | Generate an image from a text prompt using Pollinations.ai (free, no API key). Returns saved file path and records an asset manifest row with dimensions, format, checksum, and generation history. | ares/tools/image_generate.py or image_edit.py | ARES-017 | Prioritized in roadmap
48 | image_info | Media | Get metadata about an image: dimensions, format, mode, file size, EXIF data. | ares/tools/image_generate.py or image_edit.py |  | Inventoried; no confirmed critical defect in this pass
49 | resize_image | Media | Resize an image preserving aspect ratio. Uses LANCZOS resampling and records an asset manifest row with dimensions, format, checksum, and transformation history. | ares/tools/image_generate.py or image_edit.py | ARES-018 | Prioritized in roadmap
50 | convert_image | Media | Convert image between formats (PNG, JPEG, WebP, BMP, GIF). Handles RGBA to JPEG transparency and records an asset manifest row. | ares/tools/image_generate.py or image_edit.py | ARES-019 | Prioritized in roadmap
51 | crop_image | Media | Crop a rectangular region from an image. Coordinates in pixels, right/bottom exclusive. Records an asset manifest row. | ares/tools/image_generate.py or image_edit.py | ARES-020 | Prioritized in roadmap
52 | terminal_exec | Execution | Execute a shell command with full output capture, and optionally display it in the interactive terminal panel. Use this when the user explicitly says 'run in terminal', 'show me in the terminal', or wants to see the command in the terminal panel. For normal command execution without visual terminal, use run_command instead. | ares/tools/repl.py; ares/tools/executor.py | ARES-015 | Prioritized in roadmap
53 | create_cron_job | Automation | Create a recurring scheduled job that runs a fresh Ares agent session. | ares/cron/* | ARES-021 | Prioritized in roadmap
54 | list_cron_jobs | Automation | List scheduled cron jobs and their status. | ares/cron/* |  | Inventoried; no confirmed critical defect in this pass
55 | get_cron_job | Automation | Get details for a scheduled cron job. | ares/cron/* | ARES-023 | Prioritized in roadmap
56 | update_cron_job | Automation | Update a scheduled cron job fields. | ares/cron/* | ARES-021 | Prioritized in roadmap
57 | delete_cron_job | Automation | Delete a cron job while retaining logs. | ares/cron/* |  | Inventoried; no confirmed critical defect in this pass
58 | run_cron_job_now | Automation | Trigger a cron job immediately. | ares/cron/* | ARES-022 | Prioritized in roadmap
59 | get_cron_logs | Automation | Read recent markdown logs for a cron job. | ares/cron/* |  | Inventoried; no confirmed critical defect in this pass
60 | phone_status | Phone control | PHONE TOOL — the ONLY way to check Android phone status. Do NOT use run_command with kdeconnect-cli or adb for this. Checks KDE Connect and ADB bridge health. No arguments. | ares/tools/kdeconnect_bridge.py or adb_bridge.py | ARES-024 | Prioritized in roadmap
61 | phone_get_notifications | Phone control | PHONE TOOL — the ONLY way to read Android notifications. Do NOT use run_command with kdeconnect-cli for this. Read a live snapshot of recent Android notifications via KDE Connect. Treat output as private, transient data. | ares/tools/kdeconnect_bridge.py or adb_bridge.py | ARES-025 | Prioritized in roadmap
62 | phone_search_contact | Phone control | PHONE TOOL — the ONLY way to search contacts. Do NOT use run_command with kdeconnect-cli for this. Search Android contacts synced through KDE Connect by name or number. | ares/tools/kdeconnect_bridge.py or adb_bridge.py | ARES-025 | Prioritized in roadmap
63 | phone_send_sms | Phone control | PHONE TOOL — the ONLY way to send SMS. Do NOT use run_command with kdeconnect-cli for this. Send a real SMS text message through the paired Android phone via KDE Connect. Use only when the user explicitly asks to text this recipient. | ares/tools/kdeconnect_bridge.py or adb_bridge.py |  | Inventoried; no confirmed critical defect in this pass
64 | phone_call_number | Phone control | PHONE TOOL — the ONLY way to make phone calls. Do NOT use run_command with adb for this. Place a real phone call through ADB. Never call unless the user has just explicitly asked for this exact call; confirm=true is required. | ares/tools/kdeconnect_bridge.py or adb_bridge.py |  | Inventoried; no confirmed critical defect in this pass
65 | phone_launch_app | Phone control | PHONE TOOL — the ONLY way to open an app on the phone. Do NOT use run_command with adb for this. Pass the Android package name (e.g. com.google.android.youtube, com.whatsapp, com.instagram.android). | ares/tools/kdeconnect_bridge.py or adb_bridge.py |  | Inventoried; no confirmed critical defect in this pass
66 | phone_open_url | Phone control | PHONE TOOL — the ONLY way to open a URL on the phone. Do NOT use run_command with adb for this. Opens the URL in the default browser or matching app. | ares/tools/kdeconnect_bridge.py or adb_bridge.py |  | Inventoried; no confirmed critical defect in this pass
67 | update_config | Configuration | Surgically update a single config field in ~/.ares/config.json. Reads the existing config first, updates ONLY the specified path, and writes back. Never overwrites other fields. Use dot notation for nested fields (e.g. 'phone.enabled', 'model'). | ares/config.py; ares/tools/executor.py | ARES-027 | Prioritized in roadmap
68 | get_current_datetime | Time | Get the current date and time. Returns datetime, date, time, timezone, day of week, and unix timestamp. | ares/tools/datetime_tool.py | ARES-026 | Prioritized in roadmap

## Execution Plan
Phase | Target Window | Objective | Included IDs | Entry Criteria | Exit Criteria | Primary Metric
0 — Red tests | 2-3 days | Convert every confirmed bug into a failing regression test before production changes. | BUG-001 to BUG-018 | Focused baseline recorded | Every reproduced/static defect has a deterministic test or documented platform exception | Defect reproduction coverage = 100%
1 — Trust core | Weeks 1-2 | Fix false success, rollback, execution capture, MCP semantics, web evidence, memory recall, cron/config races, and export correctness. | ARES-001, 008-016, 021-022, 027 | Phase 0 tests merged | All P0 rows pass unit + integration tests; no public tool names added | False-success rate = 0 in fault injection
2 — Precision | Weeks 3-4 | Fix editing precision, memory ranking, terminal visibility, image integrity, phone status/parsing, and timezone behavior. | ARES-002, 011, 015, 017-020, 023-026, 029 | P0 stable for 1 week | All P1 acceptance tests pass on Windows and CI fixtures | Existing-tool task success +20% on eval set
3 — Scale | Week 5 | Remove file inspection/search performance cliffs without changing the feature surface. | ARES-003 to 007, 028 | P1 green | Large-repo benchmarks meet budgets and results match reference implementations | P95 local inspection latency -50%
4 — System verification | Week 6 | Run fault-injection journeys that chain memory, research, files, execution, automation, phone, and media. | All roadmap IDs | All row-level DoD complete | Full suite green; 10 end-to-end existing-tool journeys pass; upgrade notes and rollback plan complete | Journey success >=95%, zero silent failures